## Gantt (Epic)
SNL Project Pupfish — 통합 에픽 간트 (2026)
Team: Inseong Hwang(HI) · Seungyeon Jung(SJ) · Jongho Park(JP) · Taehoon Lee(TL) ¦ 오늘 6/15 (Wk6) ¦ ◆ 베타 7/11 · 릴리즈 8/29
Epic | 에픽 / 활동 | 5/11 | 5/16 | 5/23 | 5/30 | 6/6 | 6/13 | 6/20 ◀오늘 | 6/27 | 7/4 | 7/11 | 7/18 | 7/25 | 8/1 | 8/8 | 8/15 | 8/22 | 8/29 | 9/5 | 9/12
PM | 프로젝트 관리·온보딩
DISC | 발견·프로토·스펙
UIUX | ● UI·디자인·브랜드
LC | ● Lunchie 모드
MC | ● Munchie 모드
DATA | ● 데이터·인프라·BE
ENG | ● 런치 엔진·추천 R&D
MON | ● 수익화
QA | 테스트·최적화
◆ 마일스톤 | [10 empty] | BETA | [6 empty] | REL/DUE | FEED | FEED
범례
| 완료 |  | 진행중 |  | 예정 |  | 지연 |  | 과거 단계 |  | 베타 |  | 릴리즈 |  | 피드백
※ 막대 위치는 페이즈 의존성 기반 추정 — 실제 주차로 교체하세요. ● = 백로그 에픽(LC/MC/ENG/MON/DATA/UIUX).

## Epic Codes
통합 에픽 코드 (백로그 = 간트 = WBS)
코드 | 에픽 | 백로그? | 흡수한 기존 WBS 코드
LC | Lunchie 모드 | ✅ | LC#1, CONP#1(LC)
MC | Munchie 모드 | ✅ | MC#1, CONP#1(MC)
ENG | 런치 엔진·추천 R&D | ✅ | R&D, BE(추천엔진)
MON | 수익화 | ✅ | STR(수익화 리서치)
DATA | 데이터·인프라 | ✅ | TS, DE&A, BE(DB)
UIUX | UI·디자인 | ✅ | DSGN, UI&UX
PM | 프로젝트 관리 | — 프로세스 | MGNT, TRN
DISC | 발견·프로토·스펙 | — 프로세스 | IDEA, PROTO, CONP(개념), STR(스펙)
QA | 테스트·최적화 | — 프로세스 | TEST

## Tasks (recoded)
작업 목록 — 통합 에픽 코드로 재코딩
No | Phase | Epic(통합) | 기존 코드 | Task | 담당
1 | P1 | PM | MGNT | Project Kick-off & On-boarding | All
2 | P1 | PM | MGNT | Project Outline & Set Rule | TL
3 | P1 | PM | MGNT | PM Board & Team Drive Setup | TL
4 | P1 | DISC | IDEA | Brainstorming #1 - Select Topic | All
5 | P1 | DISC | IDEA | Brainstorming #2 - Develop Topic | HI,SJ,JP
6 | P1 | DISC | PROTO | Prototyping #1 - Quick AI Proto | TL
7 | P1 | DISC | PROTO | Discussion #1 - Proto Discussion | All
8 | P1 | PM | MGNT | Project Design Board Set-up | TL
9 | P1 | DISC | CONP | Prototyping #2 | TL
10 | P1 | DISC | CONP | Conceptual Product #1 - Wireframing | TL,HI
11 | P1 | DISC | STR | Preliminary App Spec & Wireframe | TL
12 | P1 | DISC | STR | Digital Factory / Branch Conveyor Concept | TL
13 | P1 | DISC | STR | Split & Assign Branch Dev | All
13.1 | P1 | LC | CONP | LC: Group Invite & Result Sharing | TL
13.2 | P1 | LC | CONP | LC: Swiping & Tab | SJ
13.3 | P1 | MC | CONP | MC: Coursemap Editor & IG Sharing | HI
13.4 | P1 | MC | CONP | MC: Data Schema & Coursemap Filtering | JP
1 | P2 | UIUX | IDEA | App/Coursemap Idea Curating (Pinterest) | All
2 | P2 | UIUX | DSGN | Brand Concept Colour & Design | SJ
3 | P2 | UIUX | IDEA | Logo Design & UI-UX Ideation | SJ
4 | P2 | UIUX | UI&UX | App Logo Design Survey | SJ
5 | P2 | UIUX | UI&UX | Landing Page & Bottom Menu Bar | SJ
6 | P2 | UIUX | UI&UX | Swiping Motion Design | SJ
7 | P2 | UIUX | UI&UX | Map Sharing Template (Polaroid) | SJ
8 | P2 | DISC | IDEA | Decision: App Logo & Name "Lunchie Munchie" | All
1.1 | P3-1 | PM | R&D | Claude Code & Harness Eng Guide | All
1.3 | P3-1 | MON | STR | Monetization Pipeline Model Research | JP
2.1 | P3-2 | DATA | TS | App Foundation & Navigation Setup | All
2.2 | P3-2 | PM | TRN | Codex Vibecoding Env Training | HI,JP
2.3 | P3-2 | LC | CONP | Group Voting & Matching Experience | SJ,TL
2.4.1 | P3-2 | LC | LC | Group Invitation & Result Sharing | TL
2.4.2 | P3-2 | LC | LC | Swiping & Tab function | SJ
2.4.3 | P3-2 | LC | LC | Group Invitation & Filtering | JP
2.4.4 | P3-2 | LC | LC | Lunchie Merge #1 & #2 | TL,SJ
2.4.5 | P3-2 | MC | MC | Course Map Builder & Visualisation | HI
2.4.6 | P3-2 | MC | MC | Course Export & Sharing | HI
2.4.7 | P3-2 | MC | MC | Coursemap Filtering | JP
2.5 | P3-2 | MC | DE&A | Social Feed & Feed Filtering | JP,HI
2.6 | P3-2 | QA | TEST | Testing & Performance Optimisation | All
3.1 | P3-3 | DATA | BE | Database Architecture & Backend Setup | JP,HI
3.2 | P3-3 | DATA | BE | Real-Time Group Voting | JP
3.3 | P3-3 | DATA | BE | Course Map Management System | HI,JP
3.4 | P3-3 | DATA | BE | Social Feed & Engagement Backend | JP,HI
3.5 | P3-3 | ENG | BE | Recommendation Engine & External API | JP
4.1 | P3-4 | DATA | DE&A | Restaurant Data Collection & Integration | JP,HI
4.2 | P3-4 | DATA | DE&A | Data Cleaning, Standardisation & Enrichment | JP,HI
4.3 | P3-4 | DATA | DE&A | User Activity Tracking & Event Logging | JP,HI
4.4 | P3-4 | ENG | DE&A | Recommendation Feature Engineering | JP,HI
4.5 | P3-4 | DATA | DE&A | Course Map Analytics & Location Processing | JP,HI